## Front End
Task | Status | COMPLETION DATE
BASIC UI
Click to submit | COMPLETE | 2023-05-30
Code 200 message | INCOMPLETE
Info display from JS object | IN PROGRESS
app token enter | COMPLETE | 2023-05-30
STYLING
App token prompt | INCOMPLETE
BDGL Logo | INCOMPLETE
Site name | INCOMPLETE
Site icon | INCOMPLETE
INCOMPLETE
INCOMPLETE
INCOMPLETE

## Back End
Task | Status | Completion Date
Talking to GLPI
Establishing connection to API | COMPLETE | 2023-05-30
Grabbing info for single entry | COMPLETE | 2023-05-31
parse info to JS object | COMPLETE | 2023-05-31
session token | COMPLETE | 2023-05-30
Get Component Info | COMPLETE | 2023-05-31
Store session token info | COMPLETE | 2023-06-02
Get component info not hardcoding | COMPLETE | 2023-05-30
Searching via service tag | IN PROGRESS
Writing to CSV | INCOMPLETE
Import CSV | INCOMPLETE
Read CSV
Write to CSV
Mass-write to CSV