## App Dev Log
Task | Status | COMPLETION DATE
FRONT END
BASIC UI
Click to submit | COMPLETE | 2023-05-30
Code 200 message | COMPLETE | 2023-06-02
Info display from JS object | COMPLETE | 2023-06-02
app token enter | COMPLETE | 2023-05-30
Data table | COMPLETE | 2023-06-02
Notes - Screen size and general | COMPLETE | 2023-06-07
Export button not duplicating | COMPLETE | 2023-06-08
STYLING
App token prompt | COMPLETE | 2023-06-05
BDGL Logo | INCOMPLETE
Site name | COMPLETE | 2023-06-02
Site icon | COMPLETE | 2023-06-05
INCOMPLETE
INCOMPLETE
INCOMPLETE
BACK END
Talking to GLPI
Establishing connection to API | COMPLETE | 2023-05-30
Grabbing info for single entry | COMPLETE | 2023-05-31
parse info to JS object | COMPLETE | 2023-05-31
session token | COMPLETE | 2023-05-30
Get Component Info | COMPLETE | 2023-05-31
Store session token info | COMPLETE | 2023-06-02
Get component info not hardcoding | COMPLETE | 2023-05-30
Searching via service tag | COMPLETE | 2023-06-02
Accounting for 0 or 2+ drives | COMPLETE | 2023-06-08
Writing to CSV | INCOMPLETE
Import CSV | INCOMPLETE
Read CSV
Write to CSV | COMPLETE | 2023-06-02
Mass-write to CSV | COMPLETE | 2023-06-02

## Inventory
Serial | Manufacturer | Model | CPU | Memory | HDD | Screen Size
9442Q32 | Dell Inc. | Latitude E7250 | Intel(R) Core(TM) i7-5600U CPU @ 2.60GHz | 8192 | SAMSUNG SSD PM851 mSATA 256GB | 12.5 | GOOD
J703QV2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | SanDisk X600 M.2 2280 SATA 256GB | 13.3 | BAD
FJ9QLQ2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | TOSHIBA KSG60ZMV256G M.2 2280 256GB | 13.3 | BAD
H4RFJR2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | TOSHIBA KSG60ZMV256G M.2 2280 256GB | 13.3 | BAD
BBMJLQ2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | TOSHIBA KSG60ZMV256G M.2 2280 256GB | 13.3 | BAD
HRQBQV2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | SK hynix SC401 SATA 256GB | 13.3 | BAD
C484M12 | Dell Inc. | Latitude E6440 | Intel(R) Core(TM) i5-4310M CPU @ 2.70GHz | 8192 | LITEONIT LCS-180M6S-11 2.5 7mm 180GB | 13.3 | GOOD
29VM533 | Dell Inc. | Latitude 5400 | Intel(R) Core(TM) i5-8265U CPU @ 1.60GHz | 8192 | PM991 NVMe Samsung 256GB | 13.3 | BAD
5DRF3M2 | Dell Inc. | Latitude 5480 | Intel(R) Core(TM) i5-7200U CPU @ 2.50GHz | 16384 | SK hynix SC308 SATA 128GB | 13.3 | BAD
CB8NQQ2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | SK hynix SC311 SATA 256GB | 13.3 | BAD
7KW9QQ2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | TOSHIBA KSG60ZMV256G M.2 2280 256GB | 13.3 | BAD
38MTNN2 | Dell Inc. | Latitude 5580 | Intel(R) Core(TM) i5-7300U CPU @ 2.60GHz | 16384 | SK hynix SC401 SATA 256GB | 15.6 | BAD
CVJJMQ2 | Dell Inc. | Latitude 5590 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | WDC WD5000LPLX-75ZNTT0 | 15.6 | BAD
6L6RMQ2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | Micron 1100 SATA 256GB | 13.3 | BAD
H0J05S2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 8192 | No drive found | 12.5 | BAD
JR64Q32 | Dell Inc. | Latitude E7250 | No CPU found | 8192 | No drive found | 12.5 | GOOD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | BAD

## Components
Serial | Screen | Memory | HDD | Touchpad | Keyboard | Battery | Stability | Notes
9442Q32 | GOOD | GOOD | GOOD | GOOD | GOOD | GOOD | GOOD
J703QV2 | GOOD | GOOD | GOOD | GOOD | GOOD | NONE | GOOD | Bad battery, needs replacing; Keyboard has cosmetic damage on Enter, A, S, N
FJ9QLQ2 | GOOD | GOOD | GOOD | BAD | GOOD | NONE | GOOD | No battery; bad trackpad
H4RFJR2 | GOOD | GOOD | NONE | GOOD | BAD | BAD | BAD | Bad battery; random shutdowns; no esc key
BBMJLQ2 | GOOD | GOOD | GOOD | GOOD | GOOD | NONE | GOOD | No battery; no hdd
HRQBQV2 | GOOD | GOOD | GOOD | GOOD | GOOD | NONE | GOOD | No battery; USB-C cosmetic damage
C484M12 | GOOD | GOOD | GOOD | GOOD | GOOD | GOOD | GOOD | Needs cleaning and check
29VM533 | BAD | GOOD | GOOD | GOOD | GOOD | NONE | GOOD | No battery; bad screen
5DRF3M2 | GOOD | GOOD | BAD | GOOD | GOOD | NONE | GOOD | No battery; bad hdd
CB8NQQ2 | GOOD | NONE | GOOD | GOOD | BAD | NONE | GOOD | No battery; no ram; bad keyboard
7KW9QQ2 | BAD | GOOD | GOOD | GOOD | BAD | NONE | BAD | No battery; bad keyboard; front cover bulge; bad drivers
38MTNN2 | GOOD | NONE | GOOD | GOOD | GOOD | NONE | GOOD | No battery; no ram; bad ethernet; ALIAS VMNB0128
CVJJMQ2 | GOOD | GOOD | GOOD | GOOD | GOOD | NONE | GOOD | No battery; ALIAS VMNB0131
6L6RMQ2 | GOOD | GOOD | GOOD | BAD | BAD | NONE | GOOD | No battery; no j key or joystick; no trackpad buttons
H0J05S2 | NONE | NONE | NONE | BAD | BAD | NONE | BAD | Don't even bother
JR64Q32 | GOOD | GOOD | GOOD | GOOD | GOOD | GOOD | GOOD | Needs check
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0
0 | [7 empty] | 0