## App Dev Log
Task | Status | COMPLETION DATE
FRONT END
BASIC UI
Click to submit | COMPLETE | 2023-05-30
Code 200 message | COMPLETE | 2023-06-02
Info display from JS object | COMPLETE | 2023-06-02
app token enter | COMPLETE | 2023-05-30
Data table | COMPLETE | 2023-06-02
STYLING
App token prompt | COMPLETE | 2023-06-05
BDGL Logo | INCOMPLETE
Site name | COMPLETE | 2023-06-02
Site icon | COMPLETE | 2023-06-05
INCOMPLETE
INCOMPLETE
INCOMPLETE
BACK END
Talking to GLPI
Establishing connection to API | COMPLETE | 2023-05-30
Grabbing info for single entry | COMPLETE | 2023-05-31
parse info to JS object | COMPLETE | 2023-05-31
session token | COMPLETE | 2023-05-30
Get Component Info | COMPLETE | 2023-05-31
Store session token info | COMPLETE | 2023-06-02
Get component info not hardcoding | COMPLETE | 2023-05-30
Searching via service tag | COMPLETE | 2023-06-02
Writing to CSV | INCOMPLETE
Import CSV | INCOMPLETE
Read CSV
Write to CSV | COMPLETE | 2023-06-02
Mass-write to CSV | COMPLETE | 2023-06-02

## Inventory
Serial | Manufacturer | Model | CPU | Memory | HDD | Screen Size
9442Q32 | Dell Inc. | Latitude E7250 | Intel(R) Core(TM) i7-5600U CPU @ 2.60GHz | 8192 | SAMSUNG SSD PM851 mSATA 256GB | 12.5 | GOOD
J703QV2 | Dell Inc. | Latitude 5490 | Intel(R) Core(TM) i5-8250U CPU @ 1.60GHz | 16384 | SanDisk X600 M.2 2280 SATA 256GB | 13.3 | BAD
0 | 0 | 0 | 0 | 0 | 0 | 0 | GOOD
0 | 0 | 0 | 0 | 0 | 0 | 0 | GOOD
0 | 0 | 0 | 0 | 0 | 0 | 0 | GOOD
0 | 0 | 0 | 0 | 0 | 0 | 0 | GOOD
0 | 0 | 0 | 0 | 0 | 0 | 0 | GOOD
0 | 0 | 0 | 0 | 0 | 0 | 0 | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | GOOD

## Components
Serial | Screen | Memory | HDD | Touchpad | Keyboard | Battery | Notes
9442Q32 | GOOD | GOOD | GOOD | GOOD | GOOD | GOOD
J703QV2 | GOOD | GOOD | BAD | GOOD | GOOD | GOOD | Has HDD instead of SSD
0
0
0
0
0
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0